## Sheet1
No. | Date | Description | Who | Status | due date | comment
1 | 14.-08.2023 | indicate differences in the two versions of the MIgration Object list and handover to MCE | Armin Schmidt | done | 15.08.2023 | regarding to the offshore team 9 additional objkects have been added to the list, so actually we have 61 instead of 52 as lsied in the initial version
2 | 14.08.2023 | check with global team for an alternative format of data objects (XML format not handbale for MCE) | Mani | in progress | 16.08.2023
3 | 15.08.2023 | check single migration objects from list for relevance in MCE pilot and update list | MCE (Elinor/Armin ) | handed over | 18.08.2023