## GanttChart
MoneG - Pilot Overall Data Migration Schedule
Capgemini
| Project Start Date | 2023-07-31 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Team Lead | LI LI / Praveen | [6 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18
 | time axis 2023-07-31 to 2023-09-24
WBS | TASK | ASSIGN TO | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2023-07-31 to 2023-09-24
1 | Data Migration Discover |  |  |  | - |  |  | -
1.1 | Develop Data Migration Strategy | CG Global |  | 2023-03-01 | 2023-03-31 | 31 | 100% | 23
1.2 | Develop Data Migration Schedule | CG Global |  | 2023-08-02 | 2023-08-08 | 7 | 80% | 5
1.3 | Define Automated Data Migration Approach | CG Global |  | 2023-03-01 | 2023-03-31 | 31 | 100% | 23
1.4 | Define Manual Data Migration Approach | CG Global |  | 2023-03-01 | 2023-03-31 | 31 | 100% | 23
1.5 | Identify Stakeholders | MCG/CG Local |  | 2023-07-31 | 2023-08-30 | 31 | 40% | 23
1.6 | Identify Team Roles And Committes | MCG/CG Local |  | 2023-07-31 | 2023-08-30 | 31 | 40% | 23
1.7 | Identify ETL Insfrastucture | MCG |  | 2023-07-31 | 2023-08-30 | 31 | 0% | 23
1.8 | Setup S/4Hana Authorizations and Security | CG Global |  | 2023-04-03 | 2023-04-28 | 26 | 100% | 20
1.9 | Design Overall Report Template | CG Global |  | 2023-09-04 | 2023-10-02 | 29 | 0% | 21
1.9.1 | Data Extraction Report Template | CG Global |  | 2023-09-04 | 2023-10-02 | 29 | 0% | 21
1.9.2 | Data Transformation Report Template | CG Global |  | 2023-09-04 | 2023-10-02 | 29 | 0% | 21
1.9.3 | Data Load Report Template | CG Global |  | 2023-09-04 | 2023-10-02 | 29 | 0% | 21
1.9.4 | Data Post-Load Report Template | CG Global |  | 2023-09-04 | 2023-10-02 | 29 | 0% | 21
2 | Legacy Data Assessment |  |  |  | - |  |  | -
2.1 | Identify Data Source (Flat File, DB, System..) | MCG |  | 2023-07-31 | 2023-07-31 | 1 | 0% | 1
2.2 | Identify Legacy Data Object | MCG | 2.1 | 2023-07-31 | 2023-08-01 | 2 | 0% | 2
2.3 | Identify Legacy Data Object Fields | MCG | 2.2 | 2023-08-03 | 2023-08-04 | 2 | 0% | 2
2.4 | Identify Legacy Data Table Against Fields In-Scope | MCG | 2.3 | 2023-08-04 | 2023-08-07 | 4 | 0% | 2
2.5 | Assess Legacy Volume | MCG | 2.2 | 2023-08-07 | 2023-08-11 | 5 | 0% | 5
3 | Target Data Assessment |  |  |  | - |  |  | -
3.1 | Identify Target System | CG Local |  | 2023-07-31 | 2023-07-31 | 1 | 0% | 1
3.2 | Identify Target Data Object | CG Local | 3.1 | 2023-07-31 | 2023-08-18 | 19 | 0% | 15
3.2.1 | Migration Cockpit Data Object | CG Local | 3.1 | 2023-07-31 | 2023-08-11 | 12 | 0% | 10
3.2.2 | RICEWF Data Object | CG Local | 3.2.1 | 2023-08-07 | 2023-08-18 | 12 | 0% | 10
3.3 | Identify Data Object Denpendency | CG Local | 3.2 | 2023-08-08 | 2023-08-19 | 12 | 0% | 9
3.4 | Identify Data Object Load Sequence | CG Local | 3.3 | 2023-08-09 | 2023-08-20 | 12 | 0% | 8
3.5 | Identify Target Data Object Fields | CG Local | 3.2 | 2023-08-09 | 2023-08-20 | 12 | 0% | 8
3.6 | Identify Target Data Table Against Fields In-Scope | CG Local | 3.5 | 2023-08-10 | 2023-08-21 | 12 | 0% | 8
4 | Data Extraction Rule Setup |  |  |  | - |  |  | -
4.1 | Design Selective Criteria Template Against Data Fields | MCG | 2.3 | 2023-08-14 | 2023-08-15 | 2 | 0% | 2
4.2 | Define Selection Rule Against Data Fields | MCG | 2.3 | 2023-08-16 | 2023-08-17 | 2 | 0% | 2
4.3 | Document Selection Rule Against Data Fields | MCG | 4.2 | 2023-08-25 | 2023-08-29 | 5 | 0% | 3
4.4 | Re-Assess Data Volume Against Slection Rule | MCG | 4.2 | 2023-08-25 | 2023-08-31 | 7 | 0% | 5
5 | Data Cleansing Rule Setup |  |  |  | - |  |  | -
5.1 | Design Data Cleansing Rule Template Against Legacy Data Fields | MCG | 2.3 | 2023-08-15 | 2023-08-18 | 4 | 0% | 4
5.2 | Define Data Cleansing Rule Against Data Fields | MCG | 5.1 | 2023-08-21 | 2023-08-25 | 5 | 0% | 5
5.3 | Document Data Cleansing Rule Against Data Fields | MCG | 5.2 | 2023-08-25 | 2023-08-29 | 5 | 0% | 3
5.4 | Design Data Quality Rule Assement | MCG | 5.2 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
5.5 | Design Data Cleansing KPI | MCG | 5.4 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
6 | Data Transformation Rule Setup |  |  |  | - |  |  | -
6.1 | Field Mapping Template Preparation | CG Global | 3.5 | 2023-08-10 | 2023-08-24 | 15 | 100% | 11
6.1.1 | Design Field Mapping Template | CG Global | 3.5 | 2023-08-10 | 2023-08-24 | 15 | 100% | 11
6.1.2 | Pre-Identify Mapping Object | CG Global | 6.1.1 | 2023-08-10 | 2023-08-24 | 15 | 100% | 11
6.2 | Mapping Object Template Preparation | CG Global | 6.1 | 2023-08-15 | 2023-08-29 | 15 | 90% | 11
6.2.1 | Design Mapping Object Template | CG Global | 3.5 | 2023-08-15 | 2023-08-29 | 15 | 0% | 11
6.2.2 | Pre-fill Mapping Object Taget Value In Template | CG Global | 6.2.1 | 2023-08-15 | 2023-08-29 | 15 | 0% | 11
6.3 | Provide Data Tranformation Requirement Against Fields | MCG | 3.5 | 2023-08-21 | 2023-08-25 | 5 | 0% | 5
6.4 | Provide Table/Field Mapping Of Source | MCG | 2.4 | 2023-08-21 | 2023-08-25 | 5 | 0% | 5
6.5 | Provide Table/Field Mapping Of Target | CG Local | 3.6 | 2023-08-21 | 2023-08-25 | 5 | 0% | 5
6.6 | Conduct Table/Field Mapping Workshops Of Source and Target | CG Local | 6.5 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
6.7 | Conduct Data Transformation Rule Workshops | CG Local | 6.6 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
6.8 | Provide Mapping Object Value Of Source | MCG | 2.3 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
6.9 | Provide Mapping Object Value Of Target | CG Local | 3.5 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
6.10 | Conduct Data Value Mapping Workshops Of Source and Target | CG Local | 6.9 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
6.11 | Document Field Mapping Template | CG Local | 6.10 | 2023-09-04 | 2023-09-08 | 5 | 0% | 5
6.12 | Document Mapping Object Template | CG Local | 6.7 | 2023-09-04 | 2023-09-08 | 5 | 0% | 5
6.13 | Document Data Transformation FSD | CG Local | 6.11 | 2023-09-04 | 2023-09-08 | 5 | 0% | 5
6.14 | Document Data Transformation TSD | CG Global | 6.13 | 2023-09-04 | 2023-09-08 | 5 | 0% | 5
6.15 | Approve Data Transformation FSD / TSD | MCG | 6.14 | 2023-09-08 | 2023-09-08 | 1 | 0% | 1
7 | Data Construction Assessment |  |  |  | - |  |  | -
7.1 | Identify Data Contruction Data Object/Field Requirement | MCG | 6.7 | 2023-08-28 | 2023-09-01 | 5 | 0% | 5
7.2 | Assess Data Contruction Data Object/Field Scope | MCG | 7.1 | 2023-08-29 | 2023-09-04 | 7 | 0% | 5
7.3 | Assess Data Volumn Of Data Contruction Field | MCG | 7.2 | 2023-09-04 | 2023-09-11 | 8 | 0% | 6
7.4 | Design Data Contruction Strategy | MCG | 7.1 | 2023-09-05 | 2023-09-13 | 9 | 0% | 7
7.5 | Data Contruction Tool Assessment | MCG | 7.1 | 2023-09-05 | 2023-09-16 | 12 | 0% | 9
8 | Pre-Load Data Validation Rule Setup |  |  |  | - |  |  | -
8.1 | Design Data Pre-Load Validation Rule Template Against Data Fields | MCG | 6.1 | 2023-08-21 | 2023-08-25 | 5 | 0% | 5
8.2 | Define Data Pre-Load Validation Rule Against Data Fields | MCG | 8.1 | 2023-08-22 | 2023-08-28 | 7 | 0% | 5
8.3 | Document Data Pre-Load Validation Against Data Fields | MCG | 8.2 | 2023-08-23 | 2023-08-30 | 8 | 0% | 6
9 | Post-Load Data Validation Rule Setup |  |  |  | - |  |  | -
9.1 | Design Data Post-Load Validation Rule Template Against Data Fields | MCG | 6.1 | 2023-08-21 | 2023-08-25 | 5 | 0% | 5
9.2 | Define Data Post-Load Validation Rule Against Data Fields | MCG | 9.1 | 2023-08-22 | 2023-08-28 | 7 | 0% | 5
9.3 | Document Data Pre-Load Validation Against Data Fields | MCG | 9.2 | 2023-08-23 | 2023-08-30 | 8 | 0% | 6
10 | Perform Data Cleanse |  |  |  | - |  |  | -
10.1 | Identify Data Scope For Cleanse | MCG | 4.2 | 2023-09-12 | 2023-09-12 | 1 | 0% | 1
10.2 | Perform Data Cleanse | MCG | 10.1 | 2023-09-13 | 2023-09-15 | 3 | 0% | 3
10.3 | Validate Data Cleanse Results | MCG | 5.5 | 2023-09-15 | 2023-09-19 | 5 | 0% | 3
11 | Setup ETL System |  |  |  | - |  |  | -
11.1 | Setup ETL Architecture & Infrastructure | MCG | 1.7 | 2023-08-07 | 2023-08-21 | 15 | 0% | 11
11.2 | ETL Application Authorizations and Security | MCG | 11.1 | 2023-08-22 | 2023-08-25 | 4 | 0% | 4
11.3 | Setup ETL System Lanscape - Dev/Qas/Sit/Prod | MCG | 11.1 | 2023-08-22 | 2023-08-25 | 4 | 0% | 4
11.4 | Setup Source Connectivity | MCG | 2.1 | 2023-08-22 | 2023-08-25 | 4 | 0% | 4
11.5 | Test Connectivity | MCG | 11.4 | 2023-08-28 | 2023-08-30 | 3 | 0% | 3
12 | Data Construction Tool Developing |  |  |  | - |  |  | -
12.1 | Document Data Construction Tool TSD | MCG | 7.5 | 2023-09-06 | 2023-09-06 | 1 | 0% | 1
12.2 | Perform Data Contruction Table in ETL DB Developing | MCG | 12.1 | 2023-09-07 | 2023-09-08 | 2 | 0% | 2
12.3 | Perform Data Contruction Tool UI Developing | MCG | 12.2 | 2023-09-08 | 2023-09-12 | 5 | 0% | 3
12.4 | Perform Data Contruction Tool API With ETL DB Developing | MCG | 12.3 | 2023-09-11 | 2023-09-15 | 5 | 0% | 5
12.5 | Unit Test Of Data Contruction Tool | MCG | 12.4 | 2023-09-13 | 2023-09-22 | 10 | 0% | 8
12.6 | Correct Data Contruction Table (Repeat Previous Task) | MCG | 12.1 | 2023-09-08 | 2023-09-22 | 15 | 0% | 11
12.7 | Authorizations and Security Of Data Contruction Tool | MCG | 12.2 | 2023-09-08 | 2023-09-08 | 1 | 0% | 1
13 | Data Extraction Developing |  |  |  | - |  |  | -
13.1 | Extract Data From Source (Flat File, DB, System...) | MCG | 4.2 | 2023-08-17 | 2023-08-17 | 1 | 0% | 1
13.2 | Document Data Extraction TSD | MCG | 4.3 | 2023-08-30 | 2023-08-30 | 1 | 0% | 1
13.3 | Perform Data Extraction Developing | MCG | 13.2 | 2023-09-04 | 2023-09-08 | 5 | 0% | 5
13.4 | Unit Test Of Data Extraction | MCG | 13.3 | 2023-09-06 | 2023-09-12 | 7 | 0% | 5
13.5 | Correct Extraction Rule (Repeat Previous Task) | MCG | 4.2 | 2023-08-25 | 2023-08-30 | 6 | 0% | 4
13.6 | Populate Data Extraction Report | MCG | 13.4 | 2023-09-12 | 2023-09-12 | 1 | 0% | 1
14 | Data Transformation Developing |  |  |  | - |  |  | -
14.1 | Setup & Test Connection | CG Global | 11.4 | 2023-09-15 | 2023-09-15 | 1 | 0% | 1
14.2 | Perform Data Transformation Developing | CG Global | 6.14 | 2023-09-15 | 2023-11-03 | 50 | 0% | 36
14.3 | Unit Test Of Data Transformation | CG Global | 14.2 | 2023-09-17 | 2023-11-05 | 50 | 0% | 35
14.4 | Correct Transformation Rule (Repeat Previous Task) | CG Global | 6.7 | 2023-11-06 | 2023-11-15 | 10 | 0% | 8
14.5 | Populate Data Transformation Report | CG Global | 14.2 | 2023-11-16 | 2023-11-17 | 2 | 0% | 2
15 | Pre-Load Data Validation Developing |  |  |  | - |  |  | -
15.1 | Setup & Test Connection | MCG | 11.4 | 2023-09-15 | 2023-09-15 | 1 | 0% | 1
15.2 | Document Data Pre-Load Validation TSD | MCG | 8.3 | 2023-09-15 | 2023-09-16 | 2 | 0% | 1
15.3 | Perform Data Pre-Load Validation Developing | MCG | 15.2 | 2023-10-30 | 2023-11-07 | 9 | 0% | 7
15.4 | Unit Test Of Data Pre-Load Validation | MCG | 15.3 | 2023-11-07 | 2023-11-15 | 9 | 0% | 7
15.5 | Correct Pre-Load Validation Rule (Repeat Previous Task) | MCG | 8.2 | 2023-11-15 | 2023-11-16 | 2 | 0% | 2
15.6 | Generate Data Pre-Load Validation Report | MCG | 15.3 | 2023-11-16 | 2023-11-16 | 1 | 0% | 1
16 | Data Load Tool Setup |  |  |  | - |  |  | -
16.1 | Setup Load Tool Authorizations and Security | CG Global | 1.8 | 2023-09-15 | 2023-09-15 | 1 | 0% | 1
16.2 | Load Tool Preparation | CG Global | 3.2 | 2023-09-18 | 2023-09-22 | 5 | 0% | 5
16.2.1 | Migration Cockpit | CG Global | 3.2.1 | 2023-09-18 | 2023-09-18 | 1 | 0% | 1
16.2.2 | LSMW - BAPI/IDOC/DIRECT INPUT/RECORDING | CG Global | 3.2.2 | 2023-09-19 | 2023-09-19 | 1 | 0% | 1
16.2.3 | Custom Program | CG Global | 3.2 | 2023-09-19 | 2023-09-19 | 1 | 0% | 1
16.3 | Document Ricewf Data Load Tool FSD | CG Global | 3.6 | 2023-09-20 | 2023-09-20 | 1 | 0% | 1
16.4 | Document Ricewf Data Load Tool TSD | CG Global | 16.3 | 2023-09-21 | 2023-09-21 | 1 | 0% | 1
16.5 | Perform Ricewf Data Load Tool Developing | CG Global | 16.4 | 2023-09-22 | 2023-09-26 | 5 | 0% | 3
16.6 | Test Ricewf Data Object Load Tool | CG Global | 16.5 | 2023-09-26 | 2023-09-29 | 4 | 0% | 4
16.7 | Load Template Preparation | CG Global | 16.5 | 2023-09-26 | 2023-09-29 | 4 | 0% | 4
16.8 | Migration Cockpit Load Tool Test | CG Global | 16.2.1 | 2023-09-19 | 2023-09-29 | 11 | 0% | 9
17 | Post-Load Data Validation Developing |  |  |  | - |  |  | -
17.1 | Setup & Test Connection | MCG | 11.4 | 2023-09-18 | 2023-09-18 | 1 | 0% | 1
17.2 | Document Data Post-Load Validation TSD | MCG | 9.3 | 2023-09-19 | 2023-09-19 | 1 | 0% | 1
17.3 | Perform Data Post-Load Validation Developing | MCG | 17.2 | 2023-10-02 | 2023-10-11 | 10 | 0% | 8
17.4 | Unit Test Of Data Post-Load Validation | MCG | 17.3 | 2023-10-04 | 2023-10-13 | 10 | 0% | 8
17.5 | Correct Post-Load Validation Rule (Repeat Previous Task) | MCG | 9.2 | 2023-10-13 | 2023-10-14 | 2 | 0% | 1
17.6 | Generate Data Post-Load Validation Report | MCG | 17.3 | 2023-10-17 | 2023-10-17 | 1 | 0% | 1
18 | Data Mock1 |  |  |  | - |  |  | -
18.1 | Setup Data Mock1 Syst. Env. | CG Global | 1.8 | 2023-11-13 | 2023-11-13 | 1 | 0% | 1
18.2 | Design Data Mock1 Load Plan | CG Local | 3.4 | 2023-11-15 | 2023-11-17 | 3 | 0% | 3
18.3 | Perform Data Construction Data Input | MCG | 12.4 | 2023-11-20 | 2023-11-22 | 3 | 0% | 3
18.4 | Perform Data Extraction Job For 40% Real Data | MCG | 13.3 | 2023-11-22 | 2023-11-24 | 3 | 0% | 3
18.5 | Populate Data Extraction Report | MCG | 18.4 | 2023-11-22 | 2023-11-24 | 3 | 0% | 3
18.6 | Perform Data Transformation Job | CG Global | 14.2 | 2023-11-27 | 2023-12-01 | 5 | 0% | 5
18.7 | Populate Data Transformation Report | CG Global | 18.6 | 2023-12-01 | 2023-12-01 | 1 | 0% | 1
18.8 | Perform Data Pre-Load Validation Job | MCG | 17.3 | 2023-12-04 | 2023-12-06 | 3 | 0% | 3
18.9 | Generate Data Pre-Load Validation Report | MCG | 18.8 | 2023-12-06 | 2023-12-06 | 1 | 0% | 1
18.10 | Perform Data Load | CG Global | 16.7 | 2023-12-07 | 2023-12-11 | 5 | 0% | 3
18.11 | Populate Data Load Report | CG Global | 18.10 | 2023-12-11 | 2023-12-11 | 1 | 0% | 1
18.12 | Perform Data Post-Load Validation Job | MCG | 17.3 | 2023-12-12 | 2023-12-14 | 3 | 0% | 3
18.13 | Generate Data Post-Load Validation Report | MCG | 18.12 | 2023-12-14 | 2023-12-14 | 1 | 0% | 1
18.14 | Raise Defect In Any Phase | MCG/CG | 18 | 2023-11-20 | 2023-12-15 | 26 | 0% | 20
18.15 | Defect Remediation | MCG/CG | 18.14 | 2023-11-20 | 2023-12-15 | 26 | 0% | 20
19 | Data Mock2 |  |  |  | - |  |  | -
19.1 | Setup Data Mock2 Syst. Env. | CG Global | 1.8 | 2023-12-18 | 2023-12-18 | 1 | 0% | 1
19.2 | Design Data Mock2 Load Plan | CG Local | 3.4 | 2023-12-19 | 2023-12-22 | 4 | 0% | 4
19.3 | Perform Data Construction Data Input | MCG | 12.4 | 2024-01-08 | 2024-01-08 | 1 | 0% | 1
19.4 | Perform Data Extraction Job For 70% Real Data | MCG | 13.3 | 2024-01-09 | 2024-01-11 | 3 | 0% | 3
19.5 | Populate Data Extraction Report | MCG | 19.4 | 2024-01-11 | 2024-01-11 | 1 | 0% | 1
19.6 | Perform Data Transformation Job | CG Global | 14.2 | 2024-01-12 | 2024-01-16 | 5 | 0% | 3
19.7 | Populate Data Transformation Report | CG Global | 19.6 | 2024-01-16 | 2024-01-16 | 1 | 0% | 1
19.8 | Perform Data Pre-Load Validation Job | MCG | 17.3 | 2024-01-17 | 2024-01-19 | 3 | 0% | 3
19.9 | Generate Data Pre-Load Validation Report | MCG | 19.8 | 2024-01-19 | 2024-01-19 | 1 | 0% | 1
19.10 | Perform Data Load | CG Global | 16.7 | 2024-01-22 | 2024-01-24 | 3 | 0% | 3
19.11 | Populate Data Load Report | CG Global | 19.10 | 2024-01-24 | 2024-01-24 | 1 | 0% | 1
19.12 | Perform Data Post-Load Validation Job | MCG | 17.3 | 2024-01-25 | 2024-01-26 | 2 | 0% | 2
19.13 | Generate Data Post-Load Validation Report | MCG | 19.12 | 2024-01-26 | 2024-01-26 | 1 | 0% | 1
19.14 | Raise Defect In Any Phase | MCG/CG | 19 | 2024-01-08 | 2024-01-26 | 19 | 0% | 15
19.15 | Defect Remediation | MCG/CG | 19.14 | 2024-01-08 | 2024-01-26 | 19 | 0% | 15
20 | Cutover/Production |  |  |  | - |  |  | -
20.1 | Setup Data Production Syst. Env. | CG Global | 1.8 | 2024-02-05 | 2024-02-09 | 5 | 0% | 5
20.2 | Design Data Production Load Plan | CG Local | 3.4 | 2024-02-12 | 2024-02-16 | 5 | 0% | 5
20.3 | Perform Data Construction Data Input | MCG | 12.4 | 2024-02-26 | 2024-03-01 | 5 | 0% | 5
20.4 | Perform Data Extraction Job For 100% Real Data | MCG | 13.3 | 2024-03-04 | 2024-03-08 | 5 | 0% | 5
20.5 | Populate Data Extraction Report | MCG | 20.4 | 2024-03-08 | 2024-03-08 | 1 | 0% | 1
20.6 | Perform Data Transformation Job | CG Global | 14.2 | 2024-03-11 | 2024-03-15 | 5 | 0% | 5
20.7 | Populate Data Transformation Report | CG Global | 20.6 | 2024-03-15 | 2024-03-15 | 1 | 0% | 1
20.8 | Perform Data Pre-Load Validation Job | MCG | 17.3 | 2024-03-18 | 2024-03-20 | 3 | 0% | 3
20.9 | Generate Data Pre-Load Validation Report | MCG | 20.8 | 2024-03-21 | 2024-03-21 | 1 | 0% | 1
20.10 | Perform Data Load | CG Global | 16.7 | 2024-03-22 | 2024-03-26 | 5 | 0% | 3
20.11 | Populate Data Load Report | CG Global | 20.10 | 2024-03-26 | 2024-03-26 | 1 | 0% | 1
20.12 | Perform Data Post-Load Validation Job | MCG | 17.3 | 2024-03-27 | 2024-03-29 | 3 | 0% | 3
20.13 | Generate Data Post-Load Validation Report | MCG | 20.12 | 2024-03-29 | 2024-03-29 | 1 | 0% | 1
20.14 | Raise Defect In Any Phase | MCG/CG | 20 | 2024-02-26 | 2024-03-29 | 33 | 0% | 25
20.15 | Defect Remediation | MCG/CG | 20.14 | 2024-02-26 | 2024-03-29 | 33 | 0% | 25
21 | Post Go-Live Support |  |  |  | - |  |  | -
21.1 | Hypercare Of Data Migration | CG | 20.10 | 2024-04-01 | 2024-04-30 | 30 | 0% | 22

## Task
WBS | TASK | ASSIGN TO | PREDECESSOR
1 | Data Migration Discover
1.1 | Develop Data Migration Strategy | CG Global
1.2 | Develop Data Migration Schedule | CG Global
1.3 | Define Automated Data Migration Approach | CG Global
1.4 | Define Manual Data Migration Approach | CG Global
1.5 | Identify Stakeholders | MCG/CG Local
1.6 | Identify Team Roles And Committes | MCG/CG Local
1.7 | Identify ETL Insfrastucture | MCG
1.8 | Setup S/4Hana Authorizations and Security | CG Global
1.9 | Design Overall Report Template | CG Global
1.9.1 | Data Extraction Report Template | CG Global
1.9.2 | Data Transformation Report Template | CG Global
1.9.3 | Data Load Report Template | CG Global
1.9.4 | Data Post-Load Report Template | CG Global
2 | Legacy Data Assessment
2.1 | Identify Data Source (Flat File, DB, System..) | MCG
2.2 | Identify Legacy Data Object | MCG | 2.1
2.3 | Identify Legacy Data Object Fields | MCG | 2.2
2.4 | Identify Legacy Data Table Against Fields In-Scope | MCG | 2.3
2.5 | Assess Legacy Volume | MCG | 2.2
3 | Target Data Assessment
3.1 | Identify Target System | CG Local
3.2 | Identify Target Data Object | CG Local | 3.1
3.2.1 | Migration Cockpit Data Object | CG Local | 3.1
3.2.2 | RICEWF Data Object | CG Local | 3.2.1
3.3 | Identify Data Object Denpendency | CG Local | 3.2
3.4 | Identify Data Object Load Sequence | CG Local | 3.3
3.5 | Identify Target Data Object Fields | CG Local | 3.2
3.6 | Identify Target Data Table Against Fields In-Scope | CG Local | 3.5
4 | Data Extraction Rule Setup
4.1 | Design Selective Criteria Template Against Data Fields | MCG | 2.3
4.2 | Define Selection Rule Against Data Fields | MCG | 2.3
4.3 | Document Selection Rule Against Data Fields | MCG | 4.2
4.4 | Re-Assess Data Volume Against Slection Rule | MCG | 4.2
5 | Data Cleansing Rule Setup
5.1 | Design Data Cleansing Rule Template Against Legacy Data Fields | MCG | 2.3
5.2 | Define Data Cleansing Rule Against Data Fields | MCG | 5.1
5.3 | Document Data Cleansing Rule Against Data Fields | MCG | 5.2
5.4 | Design Data Quality Rule Assement | MCG | 5.2
5.5 | Design Data Cleansing KPI | MCG | 5.4
6 | Data Transformation Rule Setup
6.1 | Field Mapping Template Preparation | CG Global | 3.5
6.1.1 | Design Field Mapping Template | CG Global | 3.5
6.1.2 | Pre-Identify Mapping Object | CG Global | 6.1.1
6.2 | Mapping Object Template Preparation | CG Global | 6.1
6.2.1 | Design Mapping Object Template | CG Global | 3.5
6.2.2 | Pre-fill Mapping Object Taget Value In Template | CG Global | 6.2.1
6.3 | Provide Data Tranformation Requirement Against Fields | MCG | 3.5
6.4 | Provide Table/Field Mapping Of Source | MCG | 2.4
6.5 | Provide Table/Field Mapping Of Target | CG Local | 3.6
6.6 | Conduct Table/Field Mapping Workshops Of Source and Target | CG Local | 6.5
6.7 | Conduct Data Transformation Rule Workshops | CG Local | 6.6
6.8 | Provide Mapping Object Value Of Source | MCG | 2.3
6.9 | Provide Mapping Object Value Of Target | CG Local | 3.5
6.10 | Conduct Data Value Mapping Workshops Of Source and Target | CG Local | 6.9
6.11 | Document Field Mapping Template | CG Local | 6.10
6.12 | Document Mapping Object Template | CG Local | 6.7
6.13 | Document Data Transformation FSD | CG Local | 6.11
6.14 | Document Data Transformation TSD | CG Global | 6.13
6.15 | Approve Data Transformation FSD / TSD | MCG | 6.14
7 | Data Construction Assessment
7.1 | Identify Data Contruction Data Object/Field Requirement | MCG | 6.7
7.2 | Assess Data Contruction Data Object/Field Scope | MCG | 7.1
7.3 | Assess Data Volumn Of Data Contruction Field | MCG | 7.2
7.4 | Design Data Contruction Strategy | MCG | 7.1
7.5 | Data Contruction Tool Assessment | MCG | 7.1
8 | Pre-Load Data Validation Rule Setup
8.1 | Design Data Pre-Load Validation Rule Template Against Data Fields | MCG | 6.1
8.2 | Define Data Pre-Load Validation Rule Against Data Fields | MCG | 8.1
8.3 | Document Data Pre-Load Validation Against Data Fields | MCG | 8.2
9 | Post-Load Data Validation Rule Setup
9.1 | Design Data Post-Load Validation Rule Template Against Data Fields | MCG | 6.1
9.2 | Define Data Post-Load Validation Rule Against Data Fields | MCG | 9.1
9.3 | Document Data Pre-Load Validation Against Data Fields | MCG | 9.2
10 | Perform Data Cleanse
10.1 | Identify Data Scope For Cleanse | MCG | 4.2
10.2 | Perform Data Cleanse | MCG | 10.1
10.3 | Validate Data Cleanse Results | MCG | 5.5
11 | Setup ETL System
11.1 | Setup ETL Architecture & Infrastructure | MCG | 1.7
11.2 | ETL Application Authorizations and Security | MCG | 11.1
11.3 | Setup ETL System Lanscape - Dev/Qas/Sit/Prod | MCG | 11.1
11.4 | Setup Source Connectivity | MCG | 2.1
11.5 | Test Connectivity | MCG | 11.4
12 | Data Construction Tool Developing
12.1 | Document Data Construction Tool TSD | MCG | 7.5
12.2 | Perform Data Contruction Table in ETL DB Developing | MCG | 12.1
12.3 | Perform Data Contruction Tool UI Developing | MCG | 12.2
12.4 | Perform Data Contruction Tool API With ETL DB Developing | MCG | 12.3
12.5 | Unit Test Of Data Contruction Tool | MCG | 12.4
12.6 | Correct Data Contruction Table (Repeat Previous Task) | MCG | 12.1
12.7 | Authorizations and Security Of Data Contruction Tool | MCG | 12.2
13 | Data Extraction Developing
13.1 | Extract Data From Source (Flat File, DB, System...) | MCG | 4.2
13.2 | Document Data Extraction TSD | MCG | 4.3
13.3 | Perform Data Extraction Developing | MCG | 13.2
13.4 | Unit Test Of Data Extraction | MCG | 13.3
13.5 | Correct Extraction Rule (Repeat Previous Task) | MCG | 4.2
13.6 | Populate Data Extraction Report | MCG | 13.4
14 | Data Transformation Developing
14.1 | Setup & Test Connection | CG Global | 11.4
14.2 | Perform Data Transformation Developing | CG Global | 6.14
14.3 | Unit Test Of Data Transformation | CG Global | 14.2
14.4 | Correct Transformation Rule (Repeat Previous Task) | CG Global | 6.7
14.5 | Populate Data Transformation Report | CG Global | 14.2
15 | Pre-Load Data Validation Developing
15.1 | Setup & Test Connection | MCG | 11.4
15.2 | Document Data Pre-Load Validation TSD | MCG | 8.3
15.3 | Perform Data Pre-Load Validation Developing | MCG | 15.2
15.4 | Unit Test Of Data Pre-Load Validation | MCG | 15.3
15.5 | Correct Pre-Load Validation Rule (Repeat Previous Task) | MCG | 8.2
15.6 | Generate Data Pre-Load Validation Report | MCG | 15.3
16 | Data Load Tool Setup
16.1 | Setup Load Tool Authorizations and Security | CG Global | 1.8
16.2 | Load Tool Preparation | CG Global | 3.2
16.2.1 | Migration Cockpit | CG Global | 3.2.1
16.2.2 | LSMW - BAPI/IDOC/DIRECT INPUT/RECORDING | CG Global | 3.2.2
16.2.3 | Custom Program | CG Global | 3.2
16.3 | Document Ricewf Data Load Tool FSD | CG Global | 3.6
16.4 | Document Ricewf Data Load Tool TSD | CG Global | 16.3
16.5 | Perform Ricewf Data Load Tool Developing | CG Global | 16.4
16.6 | Test Ricewf Data Object Load Tool | CG Global | 16.5
16.7 | Load Template Preparation | CG Global | 16.5
16.8 | Migration Cockpit Load Tool Test | CG Global | 16.2.1
17 | Post-Load Data Validation Developing
17.1 | Setup & Test Connection | MCG | 11.4
17.2 | Document Data Post-Load Validation TSD | MCG | 9.3
17.3 | Perform Data Post-Load Validation Developing | MCG | 17.2
17.4 | Unit Test Of Data Post-Load Validation | MCG | 17.3
17.5 | Correct Post-Load Validation Rule (Repeat Previous Task) | MCG | 9.2
17.6 | Generate Data Post-Load Validation Report | MCG | 17.3
18 | Data Mock1
18.1 | Setup Data Mock1 Syst. Env. | CG Global | 1.8
18.2 | Design Data Mock1 Load Plan | CG Local | 3.4
18.3 | Perform Data Construction Data Input | MCG | 12.4
18.4 | Perform Data Extraction Job For 40% Real Data | MCG | 13.3
18.5 | Populate Data Extraction Report | MCG | 18.4
18.6 | Perform Data Transformation Job | CG Global | 14.2
18.7 | Populate Data Transformation Report | CG Global | 18.6
18.8 | Perform Data Pre-Load Validation Job | MCG | 17.3
18.9 | Generate Data Pre-Load Validation Report | MCG | 18.8
18.10 | Perform Data Load | CG Global | 16.7
18.11 | Populate Data Load Report | CG Global | 18.10
18.12 | Perform Data Post-Load Validation Job | MCG | 17.3
18.13 | Generate Data Post-Load Validation Report | MCG | 18.12
18.14 | Raise Defect In Any Phase | MCG/CG | 18
18.15 | Defect Remediation | MCG/CG | 18.14
19 | Data Mock2
19.1 | Setup Data Mock2 Syst. Env. | CG Global | 1.8
19.2 | Design Data Mock2 Load Plan | CG Local | 3.4
19.3 | Perform Data Construction Data Input | MCG | 12.4
19.4 | Perform Data Extraction Job For 70% Real Data | MCG | 13.3
19.5 | Populate Data Extraction Report | MCG | 19.4
19.6 | Perform Data Transformation Job | CG Global | 14.2
19.7 | Populate Data Transformation Report | CG Global | 19.6
19.8 | Perform Data Pre-Load Validation Job | MCG | 17.3
19.9 | Generate Data Pre-Load Validation Report | MCG | 19.8
19.10 | Perform Data Load | CG Global | 16.7
19.11 | Populate Data Load Report | CG Global | 19.10
19.12 | Perform Data Post-Load Validation Job | MCG | 17.3
19.13 | Generate Data Post-Load Validation Report | MCG | 19.12
19.14 | Raise Defect In Any Phase | MCG/CG | 19
19.15 | Defect Remediation | MCG/CG | 19.14
20 | Cutover/Production
20.1 | Setup Data Production Syst. Env. | CG Global | 1.8
20.2 | Design Data Production Load Plan | CG Local | 3.4
20.3 | Perform Data Construction Data Input | MCG | 12.4
20.4 | Perform Data Extraction Job For 100% Real Data | MCG | 13.3
20.5 | Populate Data Extraction Report | MCG | 20.4
20.6 | Perform Data Transformation Job | CG Global | 14.2
20.7 | Populate Data Transformation Report | CG Global | 20.6
20.8 | Perform Data Pre-Load Validation Job | MCG | 17.3
20.9 | Generate Data Pre-Load Validation Report | MCG | 20.8
20.10 | Perform Data Load | CG Global | 16.7
20.11 | Populate Data Load Report | CG Global | 20.10
20.12 | Perform Data Post-Load Validation Job | MCG | 17.3
20.13 | Generate Data Post-Load Validation Report | MCG | 20.12
20.14 | Raise Defect In Any Phase | MCG/CG | 20
20.15 | Defect Remediation | MCG/CG | 20.14
21 | Post Go-Live Support
21.1 | Hypercare Of Data Migration | CG | 20.10

## Help (hidden)
Help
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
| • Define the task start date and duration (days) by editing the light green cells. | Input Cell
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
Note on C14: This is an example comment.