## Slide 1: Mone-G Germany Pilot Weekly status Report: October 9 – october 13

## Slide 2: Stream Status

## Slide 3: Data Migration Status Summary
On Time
Slight delay expected
Delay expected
Will lead to challenges
Overall Status |  | Global Template Phase Deliverables Local Assessment Workshop |  |  | Overall RAG | 
Activities/Tasks/Deliverables This Week (Completion Date) |  |  | Upcoming Activities/Tasks/Deliverables (Completion Date) |  |  | Status
 | Completed Alignment on data mapping template sequence with local MCE |  |  | Next 2 weeks Complete data extracts from client 550 Start data extracts from source clients 160, 420, (500 ?) Complete data mapping templates for client 550 |  | 
 | In Progress Internal Winshuttle training sessions started for indian team (30%) Data transformation and mapping templates (25%) |  |  |  |  | 
 |  |  |  | Later Complete data extracts from source clients 160, 420, (500 ?) Complete data mapping templates for clients 160,420, (500 ?) |  | 
RAID – Risk, Actions, Issues, Decisions |  | Mitigation Actions | Impact/Probability* H/M/L | Responsible | Resolution by
I | Load tool still not available | Grant access | high/high | Global team | asap
I | Data extraction on hold, because extraction tools (winshuttle) not available on legacy SAP systems | Provide tool access, provide data extracts | high/high | Global team | asap
I | Data transformation templates overdue, replanning required |  | high/high- | Local + Global DM team | asap
D | Decision on load toold, data transformation, rescheduling and depending CR needed | Meeting scheduled for Oct 16th with CG global team and MCG global | high/high- | Global team, | 16.Oct 2023
Reported by Armin Schmidt
13 October 2023